## Sheet 1
CLIENT | USER | ESCALATED_USER | TICKET_NUMBER | TICKET_CATEGORY | SEVERITY | DATE_OF_REPORT | DATE_OF_RESOLUTION | ESCALATION_TYPE | ESCALATION_RAISED_BY | IBM_ISSUE | FUNCTIONAL_TEAM | ESCALATION_TEXT | ACTION_TAKEN
DEVANLAY LACOSTE | jayabali@in.ibm.com | ajincp19@in.ibm.com | TS001530275 | S - Map Change | 3 | 2018-10-29 | 2018-10-29 | Process | Review-Satyam | Yes | MCR | Map Name missing in Subject | Map Name updated
Schneider Enterprise Resources, LLC | jayabali@in.ibm.com | ajincp19@in.ibm.com | TS001480826 | S - Map Change | 3 | 2018-10-22 | 2018-10-22 | Technical | Review-Satyam | Yes | MCR | Last iteration was a fix. | Spoke to Mapper
Albea Services SAS | jayabali@in.ibm.com | ajincp19@in.ibm.com | TS001474025 | S - Map Change | 3 | 2018-10-22 | 2018-10-22 | Process | Review-Satyam | Yes | MCR | Map Name missing in Subject | Map Name updated
Schneider Enterprise Resources, LLC | jayabali@in.ibm.com | ajincp19@in.ibm.com | TS001480826 | S - Map Change | 3 | 2018-10-18 | 2018-10-18 | Technical | Review-Satyam | Yes | MCR | Last iteration was a fix. | Spoke to Mapper
Church & Dwight Co., Inc. | jayabali@in.ibm.com | ajincp19@in.ibm.com | TS000839710 | S - Project - New Map | 4 | 2018-11-13 | 2018-11-13 | Process | Review - Sabiya | Yes | MCR | Ajin attached Sigma files to this case and published for client download | Correct workpacket was published.
Schneider | jayabali@in.ibm.com | ajincp19@in.ibm.com | TS000184990 | S - Project - New Map | 4 | 2018-11-23 | 2018-11-23 | Process | Review - Sabiya | Yes | MCR | Ajin has published another case client file in this case. | The additional work packet that was uploaded was removed.
US Xpress Enterprises, Inc. | jayabali@in.ibm.com | ajincp19@in.ibm.com | TS001693114 | S - Map Change | 3 | 2018-12-11 | 2018-12-11 | Technical | Review - Jayashree | Yes | MCR | Last iteration was a fix. | Spoke to Mapper
Whirlpool Corporation | jayabali@in.ibm.com | ajincp19@in.ibm.com | TS001428034 | S - Project - New Map | 4 | 2018-12-17 | 2018-12-17 | Process | Review - Raghav K | Yes | MCR | Client notification via e-mail was not done. Mapper - Ajin | Client was notified later via e-mail option in Salesforce
Schneider Enterprise Resources, LLC | jayabali@in.ibm.com | ajincp19@in.ibm.com | TS001710310 | S - Map Change | 3 | 2018-12-17 | 2018-12-17 | Process | Review-Satyam | Yes | MCR | Incoreect mention of "Map loaded to CTE" as Yes when in reality it was not loaded. | Discussed with Mapper to be careful
Church and Dwight | jayabali@in.ibm.com | ajincp19@in.ibm.com | TS000839710 | S - Project - New Map | 4 | 2018-12-31 | 2018-12-31 | Process | Review - Raghav K | Yes | MCR | MRS was not published to Client | MRS was later published.
Kennametal | jayabali@in.ibm.com | ajincp19@in.ibm.com | TS000982217 | S - Project - New Map | 4 | 2019-01-07 | 2019-01-07 | Process | Review - Raghav K | Yes | MCR | Ajin loaded the Map to CTE. But, in notification sent saying the map is not loaded to CTE. | Spoke to him to have him take care in subsequent notifications.
Lehigh Hanson | jayabali@in.ibm.com | ajincp19@in.ibm.com | TS001682555 | S - Project - New Map | 4 | 2019-01-25 | 2019-01-25 | Technical | Review - Raghav K | Yes | MCR | Fix induced by Ajin | Spoke to Mapper
Stanley Black & Decker, Inc | jayabali@in.ibm.com | ajincp19@in.ibm.com | TS001298860 | S - Map Change | 3 | 2019-01-22 | 2019-01-22 | Technical | Review - Jayashree | Yes | MCR | Last iteration was a fix. | Spoke to Mapper
Krono Services GmbH | jayabali@in.ibm.com | ajincp19@in.ibm.com | TS001500489 | S - Map Change | 3 | 2019-01-21 | 2019-01-21 | Technical | Review - Jayashree | Yes | MCR | Last iteration was a fix. | Spoke to Mapper
Corning Inc. | jayabali@in.ibm.com | ajincp19@in.ibm.com | TS001518717 | S - Project - New Map | 4 | 2019-02-12 | 2019-02-12 | Technical | Review - Raghav K | Yes | MCR | The total is always calculated; Unit price * quantity, mapper(Ajin) did incorrect calculation as Unit price + quantity. | Map fixed by Carol overnight
Schneider Enterprise Resources, LLC | jayabali@in.ibm.com | ajincp19@in.ibm.com | TS001874220 | S - Project - New Map | 4 | 2019-03-17 | 2019-03-17 | Technical | Review - Raghav K | Yes | MCR | Ajin missed to read all client comments and hence subject of the changes were only completed in last delivery. Now, the rest of the changes needed has been completed as well. Last Iteration is tagged as Fix. | Discussed Mapper to be careful